## Risk Management
RISK MANAGEMENT - Doctor Consultation System
ID | Risk Description | Probability of Occurrence | Risk Impact | Mitigation Strategy | Contingency Plan
RISK_001 | Data Security Breach | MEDIUM | HIGH | Encrypt sensitive data, implement authentication measures | Regular data backups, immediate response protocol in case of breach | LOW | MEDIUM | HIGH
RISK_002 | System Outage | LOW | MEDIUM | Regular maintenance | Emergency response team, backup servers to ensure minimal downtime. | ACCEPTABLE | LOW | GENERALLY UNACCEPTABLE
RISK_003 | Unauthorized Access | MEDIUM | HIGH | Strict access controls, regular security audits. | Immediate account lockdown | OK TO PROCEED | TAKE MITIGATION EFFORTS | SEEK SUPPORT
RISK_004 | Consultation Booking Errors | MEDIUM | MEDIUM | Automated booking system, double verification of appointments | Dedicated staff for manual booking, clear communication channels for error resolution.
RISK_005 | Integration Issues | LOW | MEDIUM | Thorough testing before integration, open communication with client | Backup manual processes, dedicated technical support for troubleshooting.
RISK_006 | Hardware Failure | LOW | MEDIUM | Regular hardware maintenance, extra hardware components | Quick replacement of failed hardware, temporary workaround procedures.
RISK_007 | Power Outage | LOW | MEDIUM | Uninterruptible power supply, backup power generators. | Emergency power management protocol, prioritized patient care during outage.
RISK_008 | Natural Disaster | LOW | HIGH | Disaster preparedness training, offsite data backups | Evacuation procedures, temporary relocation of services if necessary.
RISK_009 | Staff Training Issues | MEDIUM | LOW | Comprehensive training programs | Cross-training among staff, readily available training materials for reference
RISK_010 | Cyberattack | LOW | HIGH | Firewalls, antivirus software, regular security updates | Incident response team, communication plan for affected parties, cybersecurity insurance coverage
RISK_011 | Patient Privacy Breach | HIGH | MEDIUM | Following rules closely and making sure messages are encoded for security. | Immediate notification of affected patients, cooperation with regulatory authorities, mitigation of damages.

## Risk Assessment Matrix
RISK MATRIX | [6 empty] | ID | Risk Description | Impact | Probability
5x5 |  | IMPACT |  |  |  |  | RISK_001 | Data Security Breach | 3 | 5
|  | 1 | 2 | 3 | 4 | 5 | RISK_002 | System Outage | 1 | 2
PROBABILTY (LIKELIHOOD) | 1 |  | RISK_005 |  |  | RISK_008 | RISK_003 | Unauthorized Access | 3 | 5
| 2 | RISK_002 | RISK_006 |  |  | RISK_010 | RISK_004 | Consultation Booking Errors | 3 | 3
| 3 |  | RISK_007 | RISK_004 |  |  | RISK_005 | Integration Issues | 2 | 1
| 4 |  | RISK_009 RISK_011 |  |  |  | RISK_006 | Hardware Failure | 2 | 2
| 5 |  |  | RISK_001 RISK_003 |  |  | RISK_007 | Power Outage | 2 | 3
[7 empty] | RISK_008 | Natural Disaster | 5 | 1
|  | LOW | MEDIUM | HIGH |  |  | RISK_009 | Staff Training Issues | 2 | 4
|  | ACCEPTABLE | LOW | GENERALLY UNACCEPTABLE |  |  | RISK_010 | Cyberattack | 5 | 2
|  | OK TO PROCEED | TAKE MITIGATION EFFORTS | SEEK SUPPORT |  |  | RISK_011 | Patient Privacy Breach | 2 | 4

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources